## Build Tracker
NEXDYNE CONSULTING GROUP — GROWTH & MARKETING ENGINE · BUILD TRACKER
Status as of Jul 19, 2026 · All build stages complete — engine in operating mode · Playbook: growth-marketing/GROWTH_AND_MARKETING.md
# | Workstream | Key deliverables | Status | Completed | Owner | Notes
1 | Email infrastructure & deliverability | Resend domain verified · SPF/DKIM/DMARC · insights@ send+receive alias · CAN-SPAM footers | COMPLETE | Jul 18 | Claude | Reply-to routes to David's inbox
2 | Lead capture | Landing forms · Cloudflare Turnstile · leads DB + scoring · owner notifications | COMPLETE | Jul 18 | Claude | Turnstile first-load bug found & fixed
3 | Lead magnets (2 live) | SMB AI Readiness Guide (10-Q) · Operations Readiness Checklist (15-pt) · minimal-doc redesign | COMPLETE | Jul 19 | Claude | Pro design pass planned (swap = R2 key + covers)
4 | Gated delivery | Private Cloudflare R2 bucket · /api/download endpoint · soft gate — no public file URLs | COMPLETE | Jul 18 | Claude | New magnet = upload + registry entry, no deploy
5 | Landing page system | Config-driven template (HubSpot structure) · /resources hub · capture modal | COMPLETE | Jul 18 | Claude | New page = 1 config object
6 | Nurture & newsletter | Per-magnet 3-email automations (3/3/4-day) · NexDyne Insights: 5 issues banked, #01 sent | COMPLETE | Jul 19 | Claude | Issue 01 delivered to 7 warm-up contacts
7a | Traffic — on-site promo | Resources nav + hub · homepage band · CTAs on 115 articles + service pages · footer | COMPLETE | Jul 18 | Claude
7b | Traffic — LinkedIn | Company page live · founder post #1 published · 6-post queue dated thru Aug 5 · carousel PDF | COMPLETE | Jul 19 | David + Claude | Posting cadence: Tue + Thu 8–10am ET
7c | Traffic — SEO + GEO | 1,116-URL sitemap in GSC · robots.txt + llms.txt · JSON-LD schema · 3 cluster articles · AI crawlers unblocked at edge | COMPLETE | Jul 19 | Claude | Fixed legacy newco.tech/nexdyne.tech domains
OPERATING MODE — ONGOING / SCHEDULED
O1 | Domain warm-up | ~10 friendly inboxes remaining → ramp volume over 2–3 weeks | IN PROGRESS | — | David | Open · reply · not-spam · add to contacts
O2 | LinkedIn posting queue | #2 carousel Jul 22 · #3 Shadow AI Jul 24 · #4 Ops Jul 29 · #5 88% Jul 31 · #6 Regulation Aug 5 | SCHEDULED | — | David | Reply to every comment in hour 1
O3 | Newsletter cadence | 1 issue/month · 2-min freshness check · refill bank at 2 remaining | ONGOING | — | David + Claude | Issue 02 ≈ mid-Aug
O4 | Measurement | GSC Performance + GA4 + Resend opens/replies · track assessments booked, not downloads | ONGOING | — | Both | Review ~2 wks post-launch
O5 | Pro redesign of guides | Commission designers → swap PDFs (same R2 keys) + covers → re-polish cards | PLANNED | — | David | No code changes needed
O6 | Token cleanup | Revoke/tighten broad API tokens in .env after setup phase | BACKLOG | — | Both | Railway + Cloudflare + Resend full-access
KEY RESULTS: 1,116 pages discovered by Google on sitemap submission · AI crawlers unblocked (GPTBot, ClaudeBot, Perplexity…) · 7-contact warm-up audience, Issue 01 delivered 7/7 · Full playbook portable to next company